Sevaro Outpatient Neurology Clinic

Launch Framework & Operational Playbook

Strategic Context

Market Imperative

Neurology is entering a period of accelerating demand and structural strain. Aging populations, rising prevalence of chronic neurological disease, expanding therapeutic options, and increasing subspecialization have significantly increased the need for outpatient neurological care. At the same time, access to neurologists remains constrained by workforce shortages, uneven geographic distribution, long wait times, and fragmented referral and triage workflows.

Health systems are experiencing growing outpatient backlogs, delayed follow-up after ED and inpatient encounters, avoidable readmissions, prolonged length of stay (LOS), and inefficient use of highly trained specialists. Primary care teams are increasingly burdened with neurological complaints they are not equipped to triage or manage efficiently.

Traditional outpatient neurology models are not designed to scale, standardize, or integrate across acute, inpatient, outpatient, and primary care settings. This creates a clear strategic imperative to reimagine outpatient neurology as a digitally enabled, integrated extension of the health system care continuum.

Why Sevaro Should Lead

The outpatient neurology program is a top-priority growth initiative for 2026 and a natural extension of Sevaro's end-to-end virtual neurology platform. Sevaro has demonstrated the ability to operate at scale, deliver rapid specialist access, standardize care processes, and generate measurable ROI for health systems in high-acuity environments.

Unlike point solutions or narrowly focused telehealth offerings, Sevaro brings a platform-based approach spanning stroke, neurohospitalist services, APP-supported triage, analytics, and outpatient care. This enables outpatient neurology to be designed not as a standalone service, but as a coordinated extension of the broader neurological care journey.

Sevaro's strengths include physician-led clinical design, deep operational experience, strong health system relationships, and a scalable technology platform capable of supporting triage, workflows, documentation, analytics, and digital neurological assessments.

Program Objectives

- Improve outpatient triage and referral accuracy

- Create more efficient and standardized workflows

- Reduce avoidable readmissions and length of stay

- Improve continuity of care across settings

- Deliver a clear, defensible ROI for health system partners

Core Principles

- Lean teams. Clear ownership. Measurable execution.

- Speed to market before sophistication.

- ROI clarity is non-negotiable. Every client engagement must clearly define value, outcomes, and financial impact.

- Protect and preserve Sevaro's core stroke and neurohospitalist services while building the next growth engine.

- The core team is empowered to pull in additional internal resources as needed.

Phase Vision

| Phase 1: Foundation & ROI Discovery (Q1-Q2) | Phase 2: Smart Clinic (Q2-Q3) | Phase 3-4: Scale & Independence (Q4+) |
| --- | --- | --- |
| - Safe, compliant outpatient neurology via telemedicine - Leverage local staff and EHR workflows - Local hospital handles all billing - Manual triage, messaging, forms Goal: Go-live and prove value | - AI-augmented workflows - Automated note transfer - Smart AVS with titrations/red flags - SDNE development Goal: Differentiated model | - Sevaro billing capability - Insurance partnerships - Patient messaging in Synapse - Full platform independence Goal: National scale |

Outpatient Neurology Offerings Framework

Sevaro will offer four outpatient neurology care models and assess which combination best meets each hospital's clinical, operational, and strategic needs.

1. Bridge Clinic

Short-term neurological follow-up after ED or inpatient discharge. Designed to close care gaps, reduce bounce-backs, and lower readmissions through rapid access and safe transitions of care.

2. Continuity Neurology Clinic

Ongoing outpatient neurology care that may be general neurology or focused on a specific subspecialty (e.g., headache, epilepsy, movement disorders, stroke follow-up). Improves access, continuity, and long-term disease management while reducing unnecessary ED utilization and downstream leakage.

3. Specialty Neurology Clinic

Dedicated subspecialty clinics aligned with hospital priorities and patient complexity, designed to enhance quality, outcomes, and specialist efficiency.

4. Integrated Neurology–Primary Care Clinic

Embedded neurology support within primary care workflows to improve triage accuracy, referral efficiency, early neurological intervention, reduced LOS, and improved population health management.

Kickoff Team

Core Team (Execution & Design)

- Outpatient Lead: TBD

- Neurologist (Technology Focus): Steve

- Neurologist (Workflow & Process Focus): Melanie

- Senior Product Manager: Jesse Conley

- Business Dev Representative: TBD

Advisors (PRN)

- Dr. Paul Taheri – Former CEO, Yale School of Medicine

- Dr. Adam Cohen – Neurologist, Johns Hopkins; Wearables

- Dr. Mark Murray – Physician Executive, Novant

- Dr. Jenn Pary – Outpatient Neurologist

- Guru Sundar – Marketing, Abridge

- Julian Kochummen – Technology

- Dr. Rohini Kumar – Neurorehabilitation

Key Leadership Appointments (Core Team Responsibility)

- Lead Outpatient Neurologist with significant outpatient experience within the last 1–2 years

- Outpatient APP Lead to support clinical operations and scalability

Governance & Accountability

Weekly governance updates for the first 6 weeks, followed by biweekly updates thereafter, to the CEO, COO, CTO, CFO, APP Director, and Head of Growth.

This structure ensures tight alignment across clinical strategy, APP operations, technology, finance, and go-to-market execution during launch and scale.

Commercial Alignment

- Business Development team responsible for tracking and managing the outpatient hospital pipeline

- Live pipeline maintained including target systems, deal stage, decision-makers, defined use cases, and ROI hypothesis for each opportunity

Target Partner Systems

Actively explore early health system partners such as Novant, Kaiser, Ballad, and Franciscan that are aligned with access, scale, and innovation priorities.

Team Definitions & Mandates

Product Team (Synapse)

Mission: Build and maintain Synapse capabilities that enable outpatient neurology workflows.

| Area | Responsibility |
| --- | --- |
| Synapse Platform | Schedule display, documentation tools, recordkeeping, compliance features |
| Integrations | Technical interfaces with partner EHRs (schedule mirroring, future integrations) |
| AI Features | Scribe, triage, summaries, structured exam tools (phased delivery) |
| Out of Scope | Staffing decisions, site-specific workflow choices, MA training, PA processes |

Project Team (Operations)

Mission: Deploy Sevaro services at partner sites with safe, compliant, and efficient operations.

| Area | Responsibility |
| --- | --- |
| Site Deployment | Partner agreements, workflow configuration, role assignments per site |
| Staffing | Sevaro MA coverage model, physician scheduling, training programs |
| Workflow Design | Site-specific decisions: orders, messaging, forms, PA ownership |
| Clinical Content | Order sets, recommendation templates, dot phrases, triage criteria |
| Out of Scope | Synapse feature development, EHR integration engineering |

Staffing Requirements

Outpatient teleneurology requires coordinated staffing on both sides. Unlike inpatient consults where hospital staff manage most logistics, outpatient workflows require explicit role assignments.

Partner Site Staff (Local Health System)

These roles must be identified before go-live. Note: Roles may overlap — one person may cover multiple functions.

| Role | Responsibilities | Go-Live Requirement |
| --- | --- | --- |
| Clinic Administrator | Primary operational contact; escalation point; contract owner | Named contact identified |
| Scheduling Staff | Schedule patients in local EHR; manage cancellations; verify insurance | Trained on Sevaro visit types |
| Clinic MA | Room patient for video visit; collect vitals; print AVS; manage inbox (if assigned) | Trained on telemedicine workflow |
| Referral Coordinator | Process referrals; attach documentation; triage urgency | Understands referral requirements |
| Prior Auth Staff | Submit PAs for imaging, procedures, meds (if local owns) | PA ownership documented |
| IT / EHR Support | Provision EHR access; troubleshoot connectivity | EHR access provisioned |
| Billing | Process claims; manage denials; telehealth codes | Billing workflow confirmed |

Sevaro Staff (Go-Live Requirements)

| Role | Responsibilities | Go-Live Staffing |
| --- | --- | --- |
| Teleneurologist | Conduct visits; document; place orders; respond to messages | Min 1 MD credentialed; scale to volume |
| Sevaro MA | Schedule reconciliation; message triage; results; forms; PAs (if assigned) | 1 FTE per 2-3 MDs; adjust per workflow |
| Account Manager | Partner liaison; workflow config; training; escalations | 1 per site (can manage multiple post-stabilization) |
| Credentialing Team | Manage credentialing packets; track privileging; maintain licenses | Sevaro internal team; bandwidth for new sites |
| Technical Support | Synapse support; connectivity; EHR access issues | On-call during clinic hours |

Key Variable: Sevaro MA staffing depends on workflow ownership. If Sevaro owns PAs, add 0.5-1.0 FTE — neurology PA volume is high.

Billing Model

Phase 1: Local Hospital Bills

For MVP, the local health system handles all billing. Sevaro physicians are contracted providers; Sevaro does not bill or enroll with payers.

- Partner submits claims under their TIN

- Partner pays Sevaro contracted rate per visit or hourly

- Partner absorbs payer risk

- Simpler for Sevaro; no payer enrollment required

Phase 3-4: Sevaro Billing (Future)

In later phases, Sevaro may consider:

- Direct billing under Sevaro TIN

- Insurance partnerships

- Patient billing

- Would require payer enrollment in each state

Telehealth Billing Requirements (Partner Responsibility)

- Place of Service (POS) code: 02 (telehealth) or 10 (telehealth in patient's home)

- Modifier 95 (synchronous telemedicine) or GT depending on payer

- Document patient location (city, state) for state licensure compliance

- Verify payer-specific telehealth policies

Credentialing & Licensure

Critical Path Item: Credentialing typically takes 60-120 days and is the longest lead time in site deployment. Sevaro's credentialing team manages this process.

| Category | Requirements | Lead Time |
| --- | --- | --- |
| State Licensure | Active MD license in state where patient is located; verify telemedicine-specific requirements | 30-90 days (new) |
| DEA Registration | State-specific DEA if controlled substances prescribed (common in neurology) | 30-60 days |
| Hospital Privileges | Telemedicine privileges at partner facility; may leverage existing inpatient credentials | 60-120 days (new) |
| Malpractice | Coverage extends to telemedicine; state-specific requirements met | Verify with carrier |

Interstate Medical Licensure Compact (IMLC): If expanding to multiple states, consider IMLC for expedited licensure. As of 2024, 43 states participate.

Technology & Infrastructure Requirements

Partner Site Requirements

All partner sites will grant full EHR access to Sevaro providers and have adequate referral volumes.

- EHR Access: Remote access for Sevaro physicians and MA (if applicable); typically via VPN or Citrix

- Video Platform: Confirm video solution (Sevaro-provided or local EHR-integrated); patient instructions for access

- Exam Room Setup: Camera, monitor, speaker for patient side; ensure adequate lighting and privacy

- Connectivity: Stable internet (minimum 10 Mbps up/down); backup plan for outages

- Peripherals (if applicable): High-resolution camera for visual exam; digital stethoscope; otoscope

Sevaro Requirements

- Synapse: Configured for outpatient workflows; schedule mirroring operational; documentation templates loaded

- Physician Workstation: Dual monitors recommended; webcam; headset; reliable internet

- EHR Access: Credentials provisioned and tested for all users before go-live

- Communication: Secure messaging channel with partner site for real-time coordination

Training Requirements

| Audience | Training Topics | Format |
| --- | --- | --- |
| Sevaro Neurologists | Synapse outpatient documentation; local EHR navigation; order entry; video visit workflow; compliance requirements; escalation pathways | 1-2 hours live + practice visits |
| Sevaro MAs | Synapse schedule management; local EHR messaging/results; forms workflow; PA submission (if applicable); escalation to physician | 2-4 hours live + shadowing |
| Partner Scheduling | Sevaro visit types; slot structure; protected urgent slots; referral requirements; how to reach Sevaro | 30-60 min live |
| Partner Clinic MAs | Telemedicine rooming workflow; patient setup for video; vitals collection; AVS printing; exam room tech | 30-60 min live |
| Partner Referral Coord | Referral documentation requirements; urgency criteria; triage slot types; communication with Sevaro | 30 min live |

Phase 1: MVP Definition

Principle: MVP = minimum capabilities to see patients safely and compliantly. We accept manual workflows now to enable rapid deployment.

MVP Workflow Summary

For MVP, the provider workflow operates across two systems:

- Synapse: Documentation home (notes, structured data, longitudinal record, problem list, AVS generation)

- Epic (Local EHR): Prescribing, vitals review, orders, messaging, patient location

- PACS (Imaging): View images including CT, CTP, CTA, MRI, MRA, etc.

Product Team: MVP Technology

- Schedule Display: Synapse shows mirrored schedule with reason for consult, referral diagnosis, access to referral documentation. Patient schedule provided by Customer to Sevaro on a regular, scheduled cadence

- Documentation: Full outpatient note structure (CC, HPI, ROS, PMH/PSH/FHx/SHx, Meds/Allergies, Exam, Diagnostics, Assessment, Plan)

- Initial Consult & Follow-up Note Structure

- Documentation Methods: AI scribe, dictation, typing, dot phrases/auto-text

  - Base: Manual Entry

  - Ideal: AI Scribe

- Outpatient Problem List: Updated outpatient-oriented problem list (not relying solely on AI scribe to suggest diagnoses)

- Recordkeeping: Structured sections for imaging, EEG, EMG/NCS, labs, CSF, genetics with longitudinal entry – UNDER IMAGING RESULTS

- Compliance: Time-based documentation support, MDM clarity, telehealth requirements captured

- Note Transfer: Manual copy/paste into local EHR (automation is Phase 2)

- Patient Location Capture: Systematic capture of patient's physical location (city, state) for licensure and billing

- Telemedicine Consent: Verification workflow to confirm telemedicine consent captured before visit

- After Visit Summary (AVS): Auto-generated patient-friendly summary from Assessment & Plan; provider review/edit; PDF export for eFax or Epic paste

Records & Pre-Visit Preparation (MVP)

Providers need access to patient records before the visit for effective pre-visit preparation.

Connective Health Integration (Existing)

- Claims-based history + HIE data aggregated into standardized PDF

- Data auto-pulled into Synapse (integration already exists)

- Action Required: Reengage Connective Health to activate for outpatient workflow

Local Health System Records

- Referral note from referring provider

- Reason for referral

- Prior neurology notes

- Delivery: eFax through Epic OR traditional eFax to Sevaro

Pre-Visit Prep Timing

- Minimum: 48 hours before visit

- Ideal: 1 week before visit

- Provider can review Connective Health data and referral documentation; begin note preparation in advance

Clinical Decision Support & Order Sets (MVP)

Standardized order sets and recommendation sentences for common outpatient neurology diagnoses. These support physician efficiency and can be mapped into local EHRs as feasible.

Core MVP Order Sets

- Stroke/TIA follow-up

- Headache

- Seizure/epilepsy

- Peripheral neuropathy

- Radiculopathy

- Cognitive/memory complaints

Expanded Order Sets (Phase 2)

- Movement disorders

- Multiple sclerosis

- Neuromuscular

- Dizziness/vertigo

- Syncope/episodic altered awareness

Project Team: MVP Operations

- Scheduling: Local staff owns scheduling; define Sevaro MA access for reconciliation

- Orders: Sevaro neurologist places in local EHR; define written order workflow if needed

- Prescribing: Provider prescribes directly in Epic (local EHR); no Synapse prescribing for MVP

- Vitals: Local MA collects; provider reviews in Epic during visit

- Results/Messaging: Define ownership per site; escalation pathways documented; all messaging through Epic

- Forms: eFax intake; MA completes preliminary (Sevaro MA vs local — per site decision); physician completes and e-signs; local MA prints

- Safety: Auditable accountability for missed results, urgent messages

- Triage: MA-driven using flow sheet; protected slots: Urgent (2 wk), Semi-urgent (3 mo), Routine (6 mo)

- Video Failure Backup: Defined protocol for connectivity issues (phone visit capability, reschedule criteria)

After Visit Summary (AVS) — MVP Specification

Content (MVP)

- Readable summary of Assessment & Plan in patient-friendly language

- Diagnosis summary

- Plan bullets (medications, tests ordered, follow-up timing)

- Provider contact information / who to call with questions

Generation & Delivery

- Auto-generated from Assessment & Plan section of the note

- Provider can review and edit before finalizing

- Export as PDF

- Delivery: eFax to clinic for local MA to print, OR copy/paste into Epic's AVS workflow

Open Decisions (Per-Site Resolution Required)

| Decision | Options | Staffing Impact |
| --- | --- | --- |
| Schedule reconciliation | Local only / Sevaro MA | +0.1 FTE if Sevaro |
| Results/messaging | Local / Sevaro MA | +0.25-0.5 FTE if Sevaro |
| Order entry method | Direct / Written orders | Written = local transcribes |
| Prior authorizations | Local / Sevaro | +0.5-1.0 FTE if Sevaro (HIGH) |
| Forms preliminary completion | Local MA / Sevaro MA | +0.1-0.2 FTE if Sevaro |
| Visit block structure | 60/30, 40/20, 30/15 min | Affects throughput/revenue |

Go-Live Readiness Checklist

All items must be verified before first patient visit:

Contracts & Agreements

- Partner services agreement signed

- BAA (HIPAA Business Associate Agreement) executed

- Billing arrangement documented (local hospital bills; Sevaro contracted rate confirmed)

Credentialing & Licensure

- All physicians hold active state license

- Hospital privileges granted (telemedicine)

- DEA registration in state (if applicable)

- Malpractice coverage verified for telemedicine

Technology

- EHR access provisioned and tested for all Sevaro users

- Synapse configured with site-specific workflows

- Schedule mirroring operational

- Video platform tested end-to-end

- Connective Health integration active; data flowing to Synapse

- eFax workflow established for referral notes and records

- Patient location capture workflow functional

- After Visit Summary generation and PDF export tested

- Problem list and order sets loaded for core diagnoses

- Video failure backup plan documented

Staffing & Training

- Named contacts identified for all partner roles

- Sevaro staff assigned and trained

- Partner staff trained on telemedicine workflows

- Test visits completed successfully

Workflows

- All open decisions resolved and documented

- Escalation pathways defined (clinical and operational)

- Safety accountability plan in place

- Communication channels established (Sevaro ↔ Partner)

- Telemedicine consent capture process confirmed

- Pre-visit records availability process confirmed (minimum 48 hours)

- Forms workflow confirmed (preliminary completion, e-sign, printing)

- AVS delivery workflow confirmed (eFax or Epic paste)

Escalation Pathways

Clinical Escalations

| Situation | Pathway |
| --- | --- |
| Urgent patient during visit | Sevaro MD directs to ED; notifies partner clinic; documents recommendation |
| Critical result after hours | Partner site on-call contacted; Sevaro MD available for consult if needed |
| Patient no-show to urgent f/u | Sevaro MA attempts contact; escalates to Sevaro MD; documented outreach |
| Missed result (safety event) | Immediate review by Sevaro MD; patient contacted; event documented; root cause analysis |

Operational Escalations

| Situation | Pathway |
| --- | --- |
| Technical failure during visit | Sevaro tech support contacted; backup connectivity attempted; phone visit if needed; reschedule if unresolved |
| EHR access issue | Sevaro Account Manager contacts partner IT; temporary workaround if possible |
| Workflow dispute | Account Manager mediates; escalate to Clinic Administrator and Sevaro leadership if unresolved |
| Physician complaint | Account Manager + Sevaro Medical Director review; documented resolution |

Quality Metrics & KPIs

Track these metrics to evaluate Phase 1 success and readiness for Phase 2:

Operational Metrics

| Metric | Target | Frequency |
| --- | --- | --- |
| Visit completion rate | >90% scheduled visits completed | Weekly |
| No-show rate | <15% | Weekly |
| Technical failure rate | <2% visits affected | Weekly |
| Note completion time | <24 hours from visit | Weekly |
| Access to care (new patient) | Urgent <2 wk; Routine <6 wk | Monthly |

Safety Metrics

| Metric | Target | Frequency |
| --- | --- | --- |
| Results acknowledgment | 100% within 72 hours | Weekly |
| Critical result follow-up | 100% same day contact | Per event |
| Safety events | 0 preventable events | Per event + monthly review |

Satisfaction Metrics

- Patient satisfaction: Post-visit survey; target >4.5/5

- Partner satisfaction: Quarterly review with Clinic Administrator

- Physician satisfaction: Monthly check-in on workflow, tech, support

Risk Register

| Risk | Impact | Likelihood | Mitigation |
| --- | --- | --- | --- |
| Credentialing delays | High - delays launch | Medium | Start early; weekly tracking; escalate blockers |
| Low referral volume | Medium - poor ROI | Medium | Volume commitment in contract; ramp plan |
| Partner staff resistance | Medium - workflow failures | Medium | Early engagement; clear WIIFM; responsive support |
| Missed critical result | Very High - patient harm | Low | Clear ownership; daily inbox review; audit |
| Physician burnout | High - turnover | Medium | Reasonable schedules; MA support; Phase 2 efficiency |

Phase 2: Smart Clinic Transformation (Q2-Q3)

Phase 2 systematically replaces manual workflows with AI-augmented processes. Each capability is designed to reduce staffing burden, improve safety, or enhance patient outcomes.

Efficiency & Automation

- Automated Note Transfer: Eliminate copy/paste; notes flow directly to local EHR

- AI Message Triage: Intelligent routing; auto-responses for common queries; urgent escalation

- AI Pre-Visit Summaries: Automated chart review with relevant history, trends, action items

- Smart AVS Generation: AI-generated titration schedules, red flag warnings, activity guidance

- Forms Automation: AI pre-population of FMLA, disability forms from chart data

- Expanded Order Sets: Movement disorders, MS, neuromuscular, dizziness/vertigo, syncope

Access & Triage

- AI-Assisted Triage: Automated urgency scoring; dynamic slot allocation

- Structured Intake Review: Pre-visit review ensures appropriate workup ordered

- AI Scheduling Agents: Automated reminders, rescheduling, no-show follow-up

- Consult vs Longitudinal Pathways: Clear handoff protocols; automatic conversion

Clinical Quality & Safety

- Structured Neurologic Exam Module: Guided exam with documentation templates

- Clinical Scales Integration: Built-in scales (NIHSS, HIT-6, UPDRS, EDSS, MoCA) with longitudinal tracking

- Longitudinal Disease Visualization: Timeline view with AI-generated summaries

- Results Safety Net: AI monitoring of pending results; automated escalation

- Proactive Follow-Up: Automated treatment response check-ins; gap-in-care alerts

Standardized Digital Neurologic Exam (SDNE)

- XR-Based Assessment: Visual fields, eye movement tracking, coordination testing via VR/AR

- Wearable Integration: Gait analysis, tremor quantification, motor function

- Cognitive Assessment: Standardized testing with normative comparisons

- Automated Documentation: SDNE data flows directly into structured findings

- Longitudinal Comparison: Objective tracking of neurologic function over time

Technology & Discovery

- Explore wearable-enabled care models

- Evaluate Samsung wearables integration

- Refine AI-assisted triage prototype

Phase 3-4: Scale & Independence (Q4+)

Capabilities deferred to later phases for full platform independence and national scale:

Billing & Financial Independence

- Sevaro direct billing capability under Sevaro TIN

- Payer enrollment in target states

- Insurance partnerships

- Patient billing

Platform Independence

- Patient messaging directly in Synapse (not through Epic)

- AI triage of inbound patient messages

- AI agents for history collection, scheduling, follow-up

- Reduced dependency on local EHR for routine workflows

Next Steps

Immediate (This Week)

- Identify pilot site candidate and confirm interest

- Begin credentialing packets for target state

- Assign Account Manager for pilot

- Confirm Outpatient Lead appointment

Near-Term (Next 2 Weeks)

- Finalize partner agreement terms

- Identify named contacts for all partner site roles

- Resolve open workflow decisions

- Finalize Sevaro staffing model

- Product Team: Confirm MVP technology checklist including AVS capability

- Reengage Connective Health to activate outpatient workflow integration

- Develop core order sets (Stroke/TIA, Headache, Seizure, Neuropathy, Radiculopathy, Cognitive)

Pre-Launch (Week -4 to -1)

- Complete go-live checklist

- Conduct training for all users

- Test visits with internal patients

- Establish communication channels

- Schedule daily check-ins for first 2 weeks

- Define and document client-specific ROI metrics

- Verify AVS generation and delivery workflow

Appendix A: Pilot Timeline

Reference timeline for pilot site deployment:

| Week | Milestone |
| --- | --- |
| Week -12 | Partner agreement signed; credentialing packets submitted |
| Week -8 | Workflow decisions finalized; EHR access requested; staffing confirmed |
| Week -4 | Credentialing complete; EHR access provisioned; Synapse configured |
| Week -2 | Training complete; test patients scheduled; go-live checklist verified |
| Week 0 | GO-LIVE: First patient visits (limited volume) |
| Week 1-4 | Stabilization: Daily check-ins; rapid issue resolution; workflow refinement |
| Week 5-8 | Ramp: Increase to target volume; transition to weekly check-ins |
| Week 12 | Pilot review: Metrics analysis; lessons learned; decision on scale |